## Sheet1
Project Summary Costs
Labor Total (Approximate) |  | 7478.625
Furniture and Equipment |  | 40680
Project Total (Approx) |  | 48158.625
Labor Costs
HOURLY RATE
Project Manager(Romil Godha) | 45
Bob T. Adams | 38
Jessica A. Thomas | 35
Mary J. Ryan | 29
Average | 36.75
| TIME(HRS) | HOURLY RATE | ESTIMATE COST
Project Initiation:
Sponsor meeting | 2 | 36.75 | 73.5
Develop Project Charter | 4 | 36.75 | 147
Review and Approval of Project Charter | 4 | 36.75 | 147
Sit down meeting | 2 | 36.75 | 73.5
Site visit | 2 | 36.75 | 73.5
Develop a Project Feasibility study | 2.5 | 36.75 | 91.875
Design:
Measure allocated space | 1 | 36.75 | 36.75
Check connectivity in office | 1.5 | 36.75 | 55.125
Design Cable Route | 4 | 36.75 | 147
Calculate cabling requirements | 1 | 36.75 | 36.75
Obtain clients furniture requirements | 2 | 36.75 | 73.5
Design Furniture Layout | 1 | 36.75 | 36.75
Designate space for new equipments | 2 | 36.75 | 73.5
Procure materials:
Contact Vendors for materials | 2 | 36.75 | 73.5
Obtain cost quotation from vendors | 8 | 36.75 | 294
Procure 10 VoIP handsets | 0.5 | 36.75 | 18.375
Procure Kyocera multi-functional colour network printer-copier | 0.5 | 36.75 | 18.375
Procure Cisco ME3400 aggregation switch | 0.5 | 36.75 | 18.375
Procure 2 Cisco Aironet wireless access points | 0.5 | 36.75 | 18.375
Procure Linux server( MetroTech) | 0.5 | 36.75 | 18.375
Procure Cabling | 1.5 | 36.75 | 55.125
Procure Furniture | 1 | 36.75 | 36.75
Receive materials and clean space:
Receive Equipment | 3 | 36.75 | 110.25
Receive Cabling | 3 | 36.75 | 110.25
Receive Furniture | 4 | 36.75 | 147
Check quality of received material | 2.5 | 36.75 | 91.875
Check quanitity of received material | 2.5 | 36.75 | 91.875
Clean the work space | 3 | 36.75 | 110.25
Remove unnecessary equipments | 2 | 36.75 | 73.5
Installation:
Install Cabin | 8 | 36.75 | 294
Install Furniture | 8 | 36.75 | 294
Install 10 PC's | 10 | 36.75 | 367.5
Install required softwares | 5 | 36.75 | 183.75
Install 10 VoIP headsets | 5 | 36.75 | 183.75
Install specified printer | 1.5 | 36.75 | 55.125
Install Cisco ME3400 aggregation switch | 1 | 36.75 | 36.75
Install 2 new Cisco Aironet wireless access points | 4 | 36.75 | 147
Install Linux Server | 1 | 36.75 | 36.75
Connect Installations:
Connect PC's to RAID disk storage system | 2 | 36.75 | 73.5
Connect VoIP headsets to VoIP box | 2 | 36.75 | 73.5
Connect aggregation switch to main router | 2 | 36.75 | 73.5
Connect computers to aggregation switch | 2 | 36.75 | 73.5
Connect wireless access point to aggregation switch | 2 | 36.75 | 73.5
Connect printer to main network | 2 | 36.75 | 73.5
Testing:
Configure and Test each individual PC Workstation | 15 | 36.75 | 551.25
Configure and Test each individual VoIP handset | 6 | 36.75 | 220.5
Configure Wireless Access Points | 3 | 36.75 | 110.25
Test cabling | 5 | 36.75 | 183.75
Close project:
Develop final project documentation | 40 | 36.75 | 1470
Visit site for review | 2 | 36.75 | 73.5
Review official documentation | 3 | 36.75 | 110.25
Conduct lessons learned meeting | 4 | 36.75 | 147
Conduct peer evaluation | 2 | 36.75 | 73.5
Reassign resources | 4 | 36.75 | 147
Labor Total (Approximate) | 203.5 | 36.75 | 7478.625
Labor Total (Low) |  | 29 | 5901.5
Labor Total (High) |  | 45 | 9157.5
Equipment and Furniture Costs
| QUANTITY | PRICE | TOTAL
PC Workstations with monitors and software suite | 10 | 1750 | 17500
VoIP Handsets | 10 | 450 | 4500
Patch Cables | 1 | 240 | 240
Cubicle Furniture | 10 | 1275 | 12750
Kyocera Network High-speed Copier/ Printer | 1 | 2950 | 2950
Cisco Wireless Access Points | 2 | 160 | 320
Cisco ME3400 Switch | 1 | 1765 | 1765
Wall-mount patch panel to be mounted at hub area | 1 | 150 | 150
Network Wall Jacks total for all outlets needed | 1 | 240 | 240
Network Cables | 1 | 265 | 265
Equipment and Furniture Total |  |  | 40680